## Sheet1
Attachment 2 Portfolio of Ten Largest Investments in New Construction
AGENCY | Department of X
DATE | 2009-12-10
POINT OF CONTACT | Jim Wade
PHONE | 202-395-2181
EMAIL | jwade@omb.eop.gov
Investment | Description | FY 2010 Planning ($M) | FY 2010 Acquisition ($M) | FY 2010 O&M ($M) | Total Planning ($M) | Total Acquisition ($M) | Average Annual O&M ($M) | Start Date (mm-dd-yy) | End Date (mm-dd-yy) | BAC ($M) | BCWS ($M) | BCWP ($M) | ACWP ($M) | CV ($M) | CV (%) | CPI | SV ($M) | SV (%) | SPI | EAC ($M) | VAC ($M) | VAC (%) | Percent Complete (%) | Percent Spent (%)
Part 1: Major Investments in New Construction With EVM Data
Boise Field Office | New field office for inspectors | 1.25 | 40 | 0 | 2 | 75 | 1 | 2009-05-01 | 2011-02-15 | 71 | 10.75 | 9.7 | 9.8 | -0.1 | -1.031% | 0.9898 | -1.05 | -9.767% | 0.90233 | 71.732 | -0.73196 | -1.031% | 13.66% | 13.8%
Kansas City Lab | New research facility for scientists | 0 | 30 | 0 | 3 | 100 | 2 | 2009-01-15 | 2013-02-10 | 92 | 2 | 2.01 | 2.045 | -0.035 | -1.741% | 0.98289 | 0.01 | 0.5% | 1.005 | 93.602 | -1.602 | -1.741% | 2.185% | 2.223%
Equipment Warehouse | Expanded storage space for equipment | 0 | 20 | 1.15 | 1.25 | 20 | 1.5 | 2008-10-01 | 2009-12-31 | 18.1 | 15.2 | 14.78 | 16.589 | -1.809 | -12.24% | 0.89095 | -0.42 | -2.763% | 0.97237 | 20.3154 | -2.2154 | -12.24% | 81.66% | 91.65%
Italian Embassy | Construction of new embassy in Rome | 5 | 2 | 0.25 | 5 | 50 | 3.35 | 2009-10-01 | 2010-08-15 | 43.75 | 0.25 | 0.18 | 0.2 | -0.02 | -11.11% | 0.9 | -0.07 | -28% | 0.72 | 48.6111 | -4.8611 | -11.11% | 0.4114% | 0.4571%
Part 1 Subtotal |  | 6.25 | 92 | 1.4 | 11.25 | 245 | 7.85 | N/A | N/A | 224.85 | 28.2 | 26.67 | 28.634 | -1.964 | -7.364% | 0.93141 | -1.53 | -5.426% | 0.94574 | 241.4081 | -16.5581 | -7.364% | 11.86% | 12.73%
Part 2: Major Investments in New Construction Without EVM Data
Alaska Housing | Additional housing for Federal employees | 1 | 12.437 | 0.25 | 2.2 | 25 | 0.75
Boston School | Renovate five campus buildings. | 0.275 | 23 | 0 | 1.7 | 28.653 | 1.231
Louisville Hospital | Expand hospital complex. | 0 | 31.896 | 1.458 | 1.25 | 43 | 4.5
Prison | New prision facility and associated offices. | 0 | 28.548 | 4.3 | 1.75 | 31 | 6
HQ | Renovate wings 2 and 3 of national headquarters | 0.2 | 12.351 | 0 | 1.25 | 13 | 0.45
Southeast Regional Complex | Construct new regional office park | 0 | 27.895 | 1.5 | 3 | 55.75 | 1.5
Part 2 Subtotal |  | 1.475 | 136.127 | 7.508 | 11.15 | 196.403 | 14.431
TOTAL |  | 7.725 | 228.127 | 8.908 | 22.4 | 441.403 | 22.281